Meeting Exhibit 1: Sample Work Plan

To help plan your meeting, consider making a work plan like the one below. You can even print this work plan out and use it to guide your planning and implementation process.

Policy Issue: (I.E., MCKINNEY-VENTO FUNDING, RUNAWAY AND HOMELESS YOUTH ACT FUNDING, VETERANS HOMELESSNESS PROGRAMS)

Specific Ask: (I.E., HAVE YOUR MEMBER PARTICIPATE IN A SIGN-ON LETTER, SUPPORT FUNDING, OR CONTACT CONGRESSIONAL LEADERS)

Goals:

- Strengthen existing relationship (OR BUILD NEW RELATIONSHIP) with (SENATOR/REPRESENTATIVE X);

- Give the Member an idea of how policies are being implemented in their communities;

- Educate and inform congressional offices; and

- Elicit commitments from Members.

Timeline/Tasks

| Deadline | Tasks | Person Responsible |
| --- | --- | --- |
| 4-5 Weeks Prior to Ideal Time for Meeting | - Identify which elected representatives we want to meet with and when. - Create work plan and timeline. - Identify other key stakeholders we want to invite, and ask them if they would attend. |  |
| 3-4 Weeks Prior to Meeting | - Fax AND email the DC (or local, if appropriate) office a formal letter requesting a constituent meeting with the Member. Copy the staff person who works on the policy issue that we are highlighting. - A few days later, follow up on our request with a phone call to ensure receipt and progress. |  |
| 2-3 Weeks Prior to Meeting | - Continue to follow up with our point of contact in the congressional office until date/time is confirmed. |  |
| 2 Weeks Prior to Meeting | - Set an agenda for the meeting (see sample agenda). - Begin research and preparation of local materials. |  |
| 1-2 Weeks Prior to Meeting | - Prepare one-pagers and leave behinds on our programs and the policy request. - Do a practice run-through of the agenda. |  |
| 1 Week Prior to Meeting | - Confirm date and time again with congressional office. - Confirm number of attendees and give to scheduler. |  |
| During the Meeting | - Make sure attendees arrive early. - Remember to tie the conversation to the community. - Explain what specific action we want the Member to take. - Ask when and with whom we can follow up. |  |
| Within 1 Week Following the Meeting | - Send a thank you letter restating commitments made during the meeting (see sample thank you letter). - Follow up at the appropriate time with the relevant staff member on the policy issue, and answer any remaining questions. |  |